## Coverage
File | Type | Lines | Spec exists? | Existing tests | Coverage level | Priority to add tests | Notes
src/components/dashboard/dashboard_page/DashboardPage.vue | Component | 6 | Yes | 3 | Done | -
src/components/error/ErrorComponent/ErrorComponent.vue | Component | 24 | Yes | 6 | Done | -
src/components/error/ErrorModal/ErrorModal.vue | Component | 59 | Yes | 3 | Done | -
src/components/error/ForbiddenPage/ForbiddenPage.vue | Component | 30 | Yes | 4 | Done | -
src/components/error/NotFoundPage/NotFoundPage.vue | Component | 30 | Yes | 4 | Done | -
src/components/error/ServerErrorPage/ServerErrorPage.vue | Component | 34 | Yes | 2 | Thin | -
src/components/header/HeaderComponent.vue | Component | 90 | Yes | 7 | Done | -
src/components/login/forgotten_password/ForgottenPassword.vue | Component | 60 | Yes | 3 | Done | -
src/components/login/forgotten_password/forgotten_password_panel/ForgottenPasswordPanel.vue | Component | 125 | Yes | 4 | Done | -
src/components/login/forgotten_password/password_reset_done/PasswordResetDone.vue | Component | 69 | Yes | 2 | Thin | -
src/components/login/login_image/LoginImage.vue | Component | 41 | Yes | 2 | Thin | -
src/components/login/login_page/LoginPage.vue | Component | 146 | Yes | 5 | Done | -
src/components/login/login_page/login_panel/LoginPanel.vue | Component | 165 | Yes | 6 | Done | -
src/components/login/login_page/two_factor_panel/TwoFactorPanel.vue | Component | 134 | Yes | 8 | Done | -
src/components/login/password_reset/PasswordReset.vue | Component | 21 | Yes | 3 | Done | -
src/components/login/password_reset/password_reset_panel/PasswordResetPanel.vue | Component | 154 | Yes | 4 | Done | -
src/components/nav/NavComponent.vue | Component | 86 | Yes | 1 | Thin | -
src/components/nav/nav_menu/NavMenu.vue | Component | 147 | Yes | 5 | Done | -
src/components/nav/nav_menu/nav_menu_item/NavMenuItem.vue | Component | 147 | Yes | 5 | Done | -
src/components/nav/nav_menu/nav_menu_logout/NavMenuLogout.vue | Component | 57 | No | 0 | None | Medium
src/components/nav/nav_setting_menu/NavSettingMenu.vue | Component | 41 | No | 0 | None | Medium
src/components/new_object/NewObject.vue | Component | 194 | Yes | 8 | Done | -
src/components/object_components/access/AccessComponent.vue | Component | 24 | Yes | 3 | Done | -
src/components/object_components/access/assigned_users/AssignedUsers.vue | Component | 204 | Yes | 4 | Done | -
src/components/object_components/access/group_access/GroupAccess.vue | Component | 180 | No | 0 | None | High
src/components/object_components/document/DocumentComponent.vue | Component | 87 | Yes | 5 | Done | -
src/components/object_components/document/create_and_filter/CreateAndFilter.vue | Component | 148 | Yes | 2 | Thin | -
src/components/object_components/document/create_and_filter/new_folder/NewFolder.vue | Component | 135 | No | 0 | None | High
src/components/object_components/document/create_and_filter/new_link/NewLink.vue | Component | 135 | No | 0 | None | High
src/components/object_components/document/create_and_filter/upload_document/UploadDocument.vue | Component | 140 | No | 0 | None | High
src/components/object_components/document/document_list_render/DocumentListRender.vue | Component | 47 | Yes | 3 | Done | -
src/components/object_components/document/document_list_render/bread_crumbs/BreadCrumbs.vue | Component | 116 | Yes | 4 | Done | -
src/components/object_components/document/document_list_render/document_list/DocumentList.vue | Component | 180 | No | 0 | None | High
src/components/object_components/document/document_list_render/folder_list/FolderList.vue | Component | 195 | No | 0 | None | High
src/components/object_components/general_detail/GeneralDetailComponent.vue | Component | 249 | No | 0 | None | High
src/components/object_components/link_objects/LinkObjects.vue | Component | 175 | Yes | 5 | Done | -
src/components/object_components/link_objects/add_relationship/AddRelationship.vue | Component | 218 | Yes | 4 | Done | -
src/components/object_components/link_objects/link_objects_table/LinkObjectsTable.vue | Component | 203 | Yes | 5 | Done | -
src/components/object_components/link_objects/relationship_link/RelationshipLink.vue | Component | 169 | No | 0 | None | High
src/components/object_components/notes/NotesComponent.vue | Component | 276 | No | 0 | None | High
src/components/object_components/notes/note_list/NoteList.vue | Component | 155 | Yes | 4 | Done | -
src/components/object_components/object_priority/ObjectPriority.vue | Component | 138 | No | 0 | None | High
src/components/object_components/object_status/ObjectStatus.vue | Component | 109 | No | 0 | None | High
src/components/object_components/properties_component/PropertiesComponent.vue | Component | 410 | Yes | 2 | Thin | Medium | Existing spec is thin for the size of the component
src/components/object_components/public_links/PublicLinks.vue | Component | 239 | Yes | 2 | Thin | Medium | Existing spec is thin for the size of the component
src/components/object_components/public_links/public_link_row/PublicLinkRow.vue | Component | 92 | No | 0 | None | High
src/components/object_components/skeletons/SmallLoadingSkeleton.vue | Component | 16 | Yes | 2 | Thin | -
src/components/object_components/sprint_links/SprintLinks.vue | Component | 285 | No | 0 | None | High
src/components/object_components/sprint_links/sprint_link/SprintLink.vue | Component | 79 | Yes | 2 | Thin | -
src/components/object_components/stakeholder/StakeholderComponent.vue | Component | 91 | No | 0 | None | High
src/components/object_components/stakeholder/stakeholder_customer/StakeholderCustomer.vue | Component | 134 | Yes | 3 | Done | -
src/components/object_components/stakeholder/stakeholder_organisation/StakeholderOrganisation.vue | Component | 138 | No | 0 | None | High
src/components/prefab/add_object/AddObject.vue | Component | 108 | Yes | 7 | Done | -
src/components/prefab/object_id_tag/ObjectIdTag.vue | Component | 36 | Yes | 5 | Done | -
src/components/prefab/object_status_tag/ObjectStatusTag.vue | Component | 59 | Yes | 5 | Done | -
src/components/project/ProjectPage.vue | Component | 162 | Yes | 7 | Done | -
src/components/search/SearchPage.vue | Component | 22 | Yes | 1 | Thin | -
src/components/search/search_filter/SearchFilter.vue | Component | 195 | No | 0 | None | High
src/components/search/search_filter/search_input/SearchInput.vue | Component | 46 | Yes | 3 | Done | -
src/components/search/search_results/SearchResults.vue | Component | 42 | Yes | 2 | Thin | -
src/components/search/search_results/search_card/SearchCard.vue | Component | 93 | Yes | 3 | Done | -
src/components/search/search_results/search_header/SearchHeader.vue | Component | 56 | Yes | 4 | Done | -
src/components/skip_links/SkipLinks.vue | Component | 72 | Yes | 4 | Done | -
src/components/structure/AppStructure.vue | Component | 64 | Yes | 3 | Done | -
src/components/structure/structure_skeleton/StructureSkeleton.vue | Component | 86 | Yes | 5 | Done | -
src/composables/failedValidation.ts | Composable | 11 | No | 0 | None | High | Pure function, used by forms
src/composables/getCsrfToken.ts | Composable | 8 | No | 0 | None | High | Pure function, used by every POST
src/i18n.ts | Entry | 14 | No | 0 | None | Low
src/login.ts | Entry | 13 | No | 0 | None | Low
src/main.ts | Entry | 15 | No | 0 | None | Low | Excluded from coverage
src/pages/app/App.vue | Page | 31 | Yes | 4 | Done | -
src/pages/login_app/LoginApp.vue | Page | 27 | Yes | 3 | Done | -
src/router/loginRouter.ts | Router | 42 | No | 0 | None | Low | Fallback redirect only
src/router/router.ts | Router | 219 | No | 0 | None | High | Route guard = frontend permission gate
src/stores/documentation/documentation.ts | Store | 91 | Yes | 1 | Thin | -
src/stores/error/error.ts | Store | 20 | No | 0 | None | Medium | Used by ErrorModal
src/stores/nav/nav.ts | Store | 15 | Yes | 2 | Thin | -
src/stores/object/object.ts | Store | 92 | Yes | 1 | Thin | -
src/stores/object_meta_data/object_meta_data.ts | Store | 58 | No | 0 | None | High | Getter + filters used across object pages
src/stores/permissions/permission.ts | Store | 127 | Yes | 5 | Done | -
src/stores/search/search.ts | Store | 18 | Yes | 2 | Thin | -
src/stores/user/user.ts | Store | 15 | No | 0 | None | High | Looks broken - see Findings
src/utils/dictionary/ShortObjectDictionary.ts | Util | 13 | No | 0 | None | Low | Static map
src/utils/enums/ObjectStateEnum.ts | Util | 9 | No | 0 | None | Medium
src/utils/enums/ObjectTitleCaseEnums.ts | Util | 13 | No | 0 | None | Medium
src/utils/enums/ObjectTypeEnums.ts | Util | 11 | No | 0 | None | Medium

## Test Cases
ID | File under test | Test name | Setup / action | Expected result | Priority | Status
FE-001 | src/stores/permissions/permission.ts | Existing: empty data returns 0 | permissionData=[] ; _getMaximumFieldValue(any) | 0 | - | Exists
FE-002 | src/stores/permissions/permission.ts | Null permissionData | permissionData=null; _getMaximumFieldValue('project') | 0 (no throw) | Medium | To write
FE-003 | src/stores/permissions/permission.ts | Max across multiple groups | Two groups: project 1 and project 3 | maximum = 3 | High | To write
FE-004 | src/stores/permissions/permission.ts | Non-numeric field ignored | Field 'group_name' (string) | 0 | High | To write
FE-005 | src/stores/permissions/permission.ts | processPermissionData sets is_loaded | Call with sample data | is_loaded === true | High | To write
FE-006 | src/stores/permissions/permission.ts | processPermissionData sets maximumPermissions | Admin sample (all 4) | every maximum field = 4 | High | To write
FE-007 | src/stores/permissions/permission.ts | hasAdministrationPermission true | Only administration_create_user = 1 | true | High | To write
FE-008 | src/stores/permissions/permission.ts | hasAdministrationPermission false | All administration_* = 0 | false | High | To write
FE-009 | src/stores/permissions/permission.ts | userGroups built from permissionData | Two groups | [{value:'1',label:name,optGroup:''},...] | High | To write
FE-010 | src/stores/permissions/permission.ts | userGroups empty when no data | permissionData=null | [] | High | To write
FE-011 | src/stores/permissions/permission.ts | hasPermission true for level >0 | maximumPermissions.project=1; hasPermission('project') | true | High | To write
FE-012 | src/stores/permissions/permission.ts | hasPermission false for level 0 | maximumPermissions.task=0; hasPermission('task') | false | High | To write
FE-013 | src/stores/permissions/permission.ts | hasPermission unknown object defaults true | hasPermission('dashboard') | true (document this intentional default) | Medium | To write
FE-014 | src/stores/permissions/permission.ts | Getters return values | getCurrentObjectPermissions / getMaximumPermissions / getPermissionData | Return state values - currently return undefined (no `return`). See Findings | High | To write
FE-015 | src/stores/permissions/permission.ts | settings / customer / organisation maximums | Sample with customer=4, organisation=4 | maximumPermissions has no customer/organisation key - confirm router /customer, /organisation guard | Medium | To write
FE-016 | src/stores/object/object.ts | removeCustomer | customers=[{id:1},{id:2}]; removeCustomer(1) | [{id:2}] | High | To write
FE-017 | src/stores/object/object.ts | removeCustomer unknown id | removeCustomer(99) | List unchanged | Low | To write
FE-018 | src/stores/object/object.ts | removeGroup / removeUser | Same pattern as removeCustomer | Item removed only | High | To write
FE-019 | src/stores/object/object.ts | resetObject clears all state | Populate everything; resetObject() | Defaults restored; is_loaded false; organisation null (note initial value is {}) | High | To write
FE-020 | src/stores/object/object.ts | fetchArrayOfGroupIds getter | group_list=[{id:1},{id:3}] | [1,3] | High | To write
FE-021 | src/stores/object/object.ts | Existing: object.spec | 1 test only | Extend with cases above | - | Exists
FE-022 | src/stores/object_meta_data/object_meta_data.ts | updateObjectStatus known destination | object_status.project=[a,b]; updateObjectStatus('project') | status = [a,b] | High | To write
FE-023 | src/stores/object_meta_data/object_meta_data.ts | updateObjectStatus unknown destination | updateObjectStatus('nope') | status = [] | High | To write
FE-024 | src/stores/object_meta_data/object_meta_data.ts | updateObjectTypes known / unknown | requirement vs 'task' | type set / [] | High | To write
FE-025 | src/stores/object_meta_data/object_meta_data.ts | fetchStatus | status=[{id:1},{id:2}]; fetchStatus(2) | [{id:2}] | High | To write
FE-026 | src/stores/object_meta_data/object_meta_data.ts | availableGroupsToAdd excludes assigned | all_groups=[1,2,3]; objectStore group ids [2] | [1,3] | High | To write
FE-027 | src/stores/object_meta_data/object_meta_data.ts | availableGroupsToAdd all assigned | All groups assigned | [] | High | To write
FE-028 | src/stores/error/error.ts | setError with Error | setError(new Error('x')) | message='x' | High | To write
FE-029 | src/stores/error/error.ts | setError with string / object / null | setError('boom'), setError(null) | message=String(value) | High | To write
FE-030 | src/stores/error/error.ts | Defaults | New store | message '' , showErrorModal false | Low | To write
FE-031 | src/stores/user/user.ts | Store exposes state | useUserStore().id / username ... | Defaults (0,'',...) - currently fails: store is defined as setup function returning {state}. See Findings | High | To write
FE-032 | src/composables/failedValidation.ts | All true | {a:true,b:true} | false | High | To write
FE-033 | src/composables/failedValidation.ts | One false | {a:true,b:false} | true | High | To write
FE-034 | src/composables/failedValidation.ts | Empty object | {} | false (confirm intended) | Medium | To write
FE-035 | src/composables/failedValidation.ts | Undefined | undefined | true (fail by default) | High | To write
FE-036 | src/composables/getCsrfToken.ts | Cookie present | document.cookie='csrftoken=abc123' | 'abc123' | High | To write
FE-037 | src/composables/getCsrfToken.ts | Cookie absent | No csrftoken cookie | '' | High | To write
FE-038 | src/composables/getCsrfToken.ts | Among other cookies | 'a=1; csrftoken=xyz; b=2' | 'xyz' | High | To write
FE-039 | src/composables/getCsrfToken.ts | Cookie value with ';' boundary | csrftoken=abc; | 'abc' (no trailing ;) | Medium | To write
FE-040 | src/router/router.ts | Guard fetches metadata when not loaded | is_loaded=false; mock fetchObjectMetaData true; navigate /project | Fetch called once; navigation continues | High | To write
FE-041 | src/router/router.ts | Guard redirects on fetch failure | Fetch returns false | Redirect to name 'server-error' | High | To write
FE-042 | src/router/router.ts | Guard skips fetch on error pages | is_loaded=false; navigate /forbidden, /not-found, /server-error | Fetch not called (avoids redirect loop) | High | To write
FE-043 | src/router/router.ts | Guard does not re-fetch when loaded | is_loaded=true | Fetch not called | High | To write
FE-044 | src/router/router.ts | Allowed destination | maximumPermissions.project=1; /project | Route resolves | High | To write
FE-045 | src/router/router.ts | Forbidden destination | maximumPermissions.project=0; /project | Redirect to 'forbidden' | High | To write
FE-046 | src/router/router.ts | Each guarded route | Loop /project,/kanban_board,/requirement,/task,/request_for_change with level 0 and 1 | 0 -> forbidden ; 1 -> allowed | High | To write
FE-047 | src/router/router.ts | Route without meta.destination | Navigate / (Dashboard) | Allowed for everyone | High | To write
FE-048 | src/router/router.ts | Store reset on every navigation | Spy resetDocumentation and resetObject | Both called once per navigation | High | To write
FE-049 | src/router/router.ts | Catch-all route | Navigate /unknown/path | Resolves to not-found (confirm line ~175) | High | To write
FE-050 | src/router/router.ts | Child routes | /project, /project/new, /project/5 | Names SearchProject, NewProject, Project; id param '5' | Medium | To write
FE-051 | src/router/router.ts | fetchObjectMetaData success | Mock axios; response with permissions, username etc | permissionStore patched + processed; object meta store patched; returns true | High | To write
FE-052 | src/router/router.ts | fetchObjectMetaData failure | Axios rejects | Returns false; error handled; no throw | High | To write
FE-053 | src/router/loginRouter.ts | Fallback redirect | Navigate /anything | Redirects to /login | Low | To write
FE-054 | src/router/loginRouter.ts | Named routes | login, forgotten-password, password-reset | Resolve to expected paths | Low | To write
FE-055 | src/components/nav/nav_setting_menu/NavSettingMenu.vue | Admin item hidden without admin permission | hasAdministrationPermission=false | Administration link not rendered | High | To write
FE-056 | src/components/nav/nav_setting_menu/NavSettingMenu.vue | Admin item shown with admin permission | hasAdministrationPermission=true | Link rendered | High | To write
FE-057 | src/components/nav/nav_menu/nav_menu_logout/NavMenuLogout.vue | Renders logout button | Mount | Button/label present | High | To write
FE-058 | src/components/nav/nav_menu/nav_menu_logout/NavMenuLogout.vue | Click logs out | Mock axios post; click | POST to logout; state LoggingOut then redirect to /login | High | To write
FE-059 | src/components/nav/nav_menu/nav_menu_logout/NavMenuLogout.vue | Logout failure | Axios rejects | Error store set / state returns to NoAction | High | To write
FE-060 | src/components/nav/nav_menu/NavMenu.vue | Menu items respect permission levels | maximumPermissions.project=0 | Project entry hidden (verify against implementation) | Medium | To write
FE-061 | src/components/object_components/notes/NotesComponent.vue | Loads notes when object loaded | is_loaded flips to true | GET /api/v1/<destination>/<id>/notes/ called | High | To write
FE-062 | src/components/object_components/notes/NotesComponent.vue | Does not load before object loaded | is_loaded=false on mount | No request | High | To write
FE-063 | src/components/object_components/notes/NotesComponent.vue | Create note | Type text, click add | POST sent with text; list refreshed; input cleared | High | To write
FE-064 | src/components/object_components/notes/NotesComponent.vue | Add disabled when empty | Empty note | Add button disabled | High | To write
FE-065 | src/components/object_components/notes/NotesComponent.vue | Hidden/disabled for read-only without additive note permission | currentObjectPermissions.project_note=0 and object level 1 | No add control (mirrors backend: level 2 needed) | High | To write
FE-066 | src/components/object_components/notes/NotesComponent.vue | Delete / edit only own notes | Notes by other user | Edit/delete not offered (backend returns 404) | High | To write
FE-067 | src/components/object_components/notes/NotesComponent.vue | API error | Axios rejects | Error store populated, UI recovers | High | To write
FE-068 | src/components/object_components/access/group_access/GroupAccess.vue | Lists assigned groups | group_list has 2 | 2 rows rendered | High | To write
FE-069 | src/components/object_components/access/group_access/GroupAccess.vue | Remove hidden when only one group | group_list length 1 | No remove button (cannot leave object with no group) | High | To write
FE-070 | src/components/object_components/access/group_access/GroupAccess.vue | Remove shown when >1 group | group_list length 2 | Remove button per row | High | To write
FE-071 | src/components/object_components/access/group_access/GroupAccess.vue | Add group shown when available groups | availableGroupsToAdd >0 | Select + add button visible | High | To write
FE-072 | src/components/object_components/access/group_access/GroupAccess.vue | No groups available message | availableGroupsToAdd=0 | 'no groups' message shown | High | To write
FE-073 | src/components/object_components/access/group_access/GroupAccess.vue | Add group success | Select group, click add | POST /groups/ ; objectStore.group_list updated | High | To write
FE-074 | src/components/object_components/access/group_access/GroupAccess.vue | Add group error | Axios rejects | errorMessage shown | High | To write
FE-075 | src/components/object_components/access/assigned_users/AssignedUsers.vue | Gap: remove user / add user error paths | Existing spec has 4 tests | Add error + empty list tests | Medium | To write
FE-076 | src/components/object_components/sprint_links/SprintLinks.vue | Loads sprints when object loaded | is_loaded true | GET sprint list | Medium | To write
FE-077 | src/components/object_components/sprint_links/SprintLinks.vue | Empty state | sprintData=[] | Empty message, no table | Medium | To write
FE-078 | src/components/object_components/sprint_links/SprintLinks.vue | List state | sprintData has rows | One SprintLink per row | Medium | To write
FE-079 | src/components/object_components/sprint_links/SprintLinks.vue | Add sprint | Select sprint, click add | POST; list refreshed | Medium | To write
FE-080 | src/components/object_components/sprint_links/SprintLinks.vue | Remove sprint | Click remove | DELETE; row removed | Medium | To write
FE-081 | src/components/object_components/general_detail/GeneralDetailComponent.vue | Update button disabled when invalid/unchanged | Empty title | Disabled | High | To write
FE-082 | src/components/object_components/general_detail/GeneralDetailComponent.vue | Update button hidden when read only | Object level 1 | No update button (mirrors PATCH min level 2) | High | To write
FE-083 | src/components/object_components/general_detail/GeneralDetailComponent.vue | Update success | Edit title, click update | PATCH sent with fields; objectStore updated | High | To write
FE-084 | src/components/object_components/general_detail/GeneralDetailComponent.vue | 403 response | Axios 403 | router.push forbidden | High | To write
FE-085 | src/components/object_components/general_detail/GeneralDetailComponent.vue | 404 response | Axios 404 | router.push not-found | High | To write
FE-086 | src/components/object_components/general_detail/GeneralDetailComponent.vue | 500 / network error | Axios 500 | router.push server-error | High | To write
FE-087 | src/components/object_components/object_priority/ObjectPriority.vue | Renders current priority | objectStore.priority set | Select shows current value | Medium | To write
FE-088 | src/components/object_components/object_priority/ObjectPriority.vue | Changing priority updates object store | Change select | objectStore.priority updated | Medium | To write
FE-089 | src/components/object_components/object_priority/ObjectPriority.vue | Select disabled when read only | Level 1 | Disabled | Medium | To write
FE-090 | src/components/object_components/object_status/ObjectStatus.vue | Renders current status | objectStore.status set | Select shows current value | Medium | To write
FE-091 | src/components/object_components/object_status/ObjectStatus.vue | Changing status updates object store | Change select | objectStore.status updated | Medium | To write
FE-092 | src/components/object_components/object_status/ObjectStatus.vue | Select disabled when read only | Level 1 | Disabled | Medium | To write
FE-093 | src/components/object_components/public_links/public_link_row/PublicLinkRow.vue | Shows id | props id='abc' | 'abc' displayed | Medium | To write
FE-094 | src/components/object_components/public_links/public_link_row/PublicLinkRow.vue | Copy link | Click first cell; mock navigator.clipboard | writeText called with <origin>/public_link/<id>/ ; 'copied' shown 2s then hidden | Medium | To write
FE-095 | src/components/object_components/public_links/public_link_row/PublicLinkRow.vue | Copy failure | clipboard rejects | No crash; status not shown | Low | To write
FE-096 | src/components/object_components/public_links/public_link_row/PublicLinkRow.vue | Active icon | isActive true / false | Check icon vs X icon | Medium | To write
FE-097 | src/components/object_components/public_links/public_link_row/PublicLinkRow.vue | Emits updateActive | Click second cell | emit('updateActive',{id,index}) | Medium | To write
FE-098 | src/components/object_components/public_links/public_link_row/PublicLinkRow.vue | Emits deleteLink | Click third cell | emit('deleteLink',{id}) | Medium | To write
FE-099 | src/components/object_components/stakeholder/StakeholderComponent.vue | Loads data when object loaded | is_loaded true | Meta data fetched (customers, organisations) | Medium | To write
FE-100 | src/components/object_components/stakeholder/StakeholderComponent.vue | No load before object loaded | is_loaded false | No request | Medium | To write
FE-101 | src/components/object_components/stakeholder/stakeholder_organisation/StakeholderOrganisation.vue | Shows organisation | organisation set | Name rendered | Medium | To write
FE-102 | src/components/object_components/stakeholder/stakeholder_organisation/StakeholderOrganisation.vue | No organisation | organisation=null | Label hidden; add selector shown | Medium | To write
FE-103 | src/components/object_components/stakeholder/stakeholder_organisation/StakeholderOrganisation.vue | Add / remove organisation | Select + click | POST / DELETE ; store updated | Medium | To write
FE-104 | src/components/object_components/document/create_and_filter/new_folder/NewFolder.vue | Submit disabled when empty | No input | Create/Upload button disabled | Medium | To write
FE-105 | src/components/object_components/document/create_and_filter/new_folder/NewFolder.vue | Submit enabled when valid | Valid input | Button enabled | Medium | To write
FE-106 | src/components/object_components/document/create_and_filter/new_folder/NewFolder.vue | Successful submit closes modal | Mock axios ok | POST made; emit('closeModal') | Medium | To write
FE-107 | src/components/object_components/document/create_and_filter/new_folder/NewFolder.vue | Cancel closes modal | Click cancel | emit('closeModal') and no request | Medium | To write
FE-108 | src/components/object_components/document/create_and_filter/new_link/NewLink.vue | Submit disabled when empty | No input | Create/Upload button disabled | Medium | To write
FE-109 | src/components/object_components/document/create_and_filter/new_link/NewLink.vue | Submit enabled when valid | Valid input | Button enabled | Medium | To write
FE-110 | src/components/object_components/document/create_and_filter/new_link/NewLink.vue | Successful submit closes modal | Mock axios ok | POST made; emit('closeModal') | Medium | To write
FE-111 | src/components/object_components/document/create_and_filter/new_link/NewLink.vue | Cancel closes modal | Click cancel | emit('closeModal') and no request | Medium | To write
FE-112 | src/components/object_components/document/create_and_filter/upload_document/UploadDocument.vue | Submit disabled when empty | No input | Create/Upload button disabled | Medium | To write
FE-113 | src/components/object_components/document/create_and_filter/upload_document/UploadDocument.vue | Submit enabled when valid | Valid input | Button enabled | Medium | To write
FE-114 | src/components/object_components/document/create_and_filter/upload_document/UploadDocument.vue | Successful submit closes modal | Mock axios ok | POST made; emit('closeModal') | Medium | To write
FE-115 | src/components/object_components/document/create_and_filter/upload_document/UploadDocument.vue | Cancel closes modal | Click cancel | emit('closeModal') and no request | Medium | To write
FE-116 | src/components/object_components/document/create_and_filter/upload_document/UploadDocument.vue | Rejects oversize / wrong file | If limits exist | Error shown | Low | To write
FE-117 | src/components/object_components/document/document_list_render/document_list/DocumentList.vue | Lists documents | documentationStore documents | One row each | Medium | To write
FE-118 | src/components/object_components/document/document_list_render/document_list/DocumentList.vue | Empty list | None | Empty state | Medium | To write
FE-119 | src/components/object_components/document/document_list_render/document_list/DocumentList.vue | Delete document | Click delete | DELETE called; row removed | Medium | To write
FE-120 | src/components/object_components/document/document_list_render/folder_list/FolderList.vue | Lists folders / click navigates | folders in store | Rows rendered; click sets current folder | Medium | To write
FE-121 | src/components/object_components/document/document_list_render/folder_list/FolderList.vue | Delete folder | Click delete | DELETE called | Medium | To write
FE-122 | src/components/object_components/link_objects/relationship_link/RelationshipLink.vue | Emits updateRelationship | Change select | emit with {index, link_relationship} | Medium | To write
FE-123 | src/components/object_components/link_objects/relationship_link/RelationshipLink.vue | Shows current relationship | props | Select value matches | Medium | To write
FE-124 | src/components/search/search_filter/SearchFilter.vue | Filter updates on route change | Change route destination | Filters reset to new destination | Medium | To write
FE-125 | src/components/search/search_filter/SearchFilter.vue | Search request | Enter term | GET search endpoint, results into search store | Medium | To write
FE-126 | src/components/search/search_filter/SearchFilter.vue | Fetch error | Axios rejects | router.push server-error | Medium | To write
FE-127 | src/components/object_components/public_links/PublicLinks.vue | Gap: create / toggle / delete + error paths | Existing spec has 2 tests | Add tests per action; read-only hides create/delete | Medium | To write
FE-128 | src/components/object_components/properties_component/PropertiesComponent.vue | Gap: 410 lines, 2 tests | Existing spec thin | Cover each property control, save, validation, read-only state | Medium | To write
FE-129 | src/components/project/ProjectPage.vue | Gap: permission states | Existing 7 tests | Read-only level 1: inputs disabled and update hidden; level 4: delete available | High | To write
FE-130 | src/components/new_object/NewObject.vue | Gap: group selection required | Existing 8 tests | No groups selected -> create disabled (backend returns 400); only permitted groups offered | High | To write
FE-131 | src/utils/dictionary/ShortObjectDictionary.ts | All keys map | Iterate ObjectTypeEnums | Every enum key has a short code | Low | To write
FE-132 | src/utils/enums/* | Enums consistent | ObjectTypeEnums keys vs ObjectTitleCaseEnums | Every type has a title (group & user extra in title) | Low | To write

## Findings
# | File | Observation | Suggested action
1 | src/stores/user/user.ts | defineStore('user', () => ({ state: () => ... })) uses a setup-store signature but returns an options-style object. The store ends up exposing a `state` function, not id/username/etc. Router sets these fields so they would be silently lost. | Convert to options store (state: () => ({...})) then add the user store tests
2 | src/stores/permissions/permission.ts | getCurrentObjectPermissions, getMaximumPermissions and getPermissionData use `state => { state.x }` with braces and no return, so they return undefined. | Add `return` (or remove braces) - the tests in FE list will catch it
3 | src/stores/permissions/permission.ts | hasPermission: `object as keyof X && ...` - the cast is always truthy; only the `in` check does work. Unknown objects return true. | Confirm default-true is intended; add test documenting it
4 | src/stores/permissions/permission.ts | maximumPermissions has no customer, organisation, sprint, tag or schedule_object. Backend decorators protect those; the frontend can't gate them. | Add fields when those pages are built
5 | src/router/router.ts | Frontend gate only checks `> 0` (any read access). Edit/add/delete levels are not checked in the UI. | Add per-object level (current object) to the permission store and tests for disabled controls at level 1, 2, 3, 4
6 | src/stores/object/object.ts | resetObject() sets organisation = null but initial state is {}. | Decide on one default; test it
7 | Whole suite | Vitest runs in a Playwright Chromium browser (vitest.config.ts). Pure logic (stores, composables) can run faster in a node/jsdom project. | Optional: add a second vitest project for non-DOM tests

## Conventions
Topic | Pattern used by existing specs
Location | Spec sits next to source: Foo.vue -> Foo.spec.ts
Imports | import {describe,test,expect,beforeEach} from 'vitest'; mount/flushPromises from @vue/test-utils
Stores | beforeEach(() => setActivePinia(createPinia())); call store actions directly
Routing | createRouter + createMemoryHistory with stub routes (see NavMenuItem.spec.ts)
Naming | describe('<Component or Store> - <thing>') ; test('plain English sentence')
Run | npm run test:unit (watch) ; npm run coverage
Per component checklist | 1 renders 2 each prop 3 each emit 4 each store-driven state 5 permission/read-only state 6 API success 7 API error 8 empty state